## PIVOTS (hidden)
Row Labels | Committed | Injected | Delivered | Row Labels | Defect Leakage. | Row Labels | Sum of Capacity Utilization | Row Labels | Sprint | Delivered SP | Flactuation | Velocity Flactuation | Row Labels | Committment Reliability. | Row Labels | Sum of Scope_Change
Sprint 1 | 35 | 21 | 22 | Sprint 1 | 73.33% | Sprint 1 | 72.46% | Avengers | Sprint 1 | 22 | 49.3333 | 80.49% | Sprint 1 | 62.86% | Sprint 1 | 95.45%
Sprint 2 | 25 | 5 | 28 | Sprint 2 | 60% | Sprint 2 | 73.84% | Grand Total | Sprint 2 | 28 | 55.3333 | 102.44% | Sprint 2 | 112% | Sprint 2 | 17.86%
Sprint 3 | 27 | 0 | 27 | Sprint 3 | 41.67% | Sprint 3 | 104.2% |  | Sprint 3 | 27 | 54.3333 | 98.78% | Sprint 3 | 100% | Sprint 3 | 0%
Sprint 4 | 29 | 0 | 29 | Sprint 4 | 27.27% | Sprint 4 | 94.94% |  | Sprint 4 | 29 | 56.3333 | 106.1% | Sprint 4 | 100% | Sprint 4 | 0%
Sprint 5 | 30 | 0 | 30 | Sprint 5 | 22.22% | Sprint 5 | 87.5% |  | Sprint 5 | 30 | 57.3333 | 109.76% | Sprint 5 | 100% | Sprint 5 | 0%
Sprint 6 | 32 | 0 | 28 | Sprint 6 | 0% | Sprint 6 | 97.22% |  | Sprint 6 | 28 | 55.3333 | 102.44% | Sprint 6 | 87.5% | Sprint 6 | -14.29%
Grand Total | 178 | 26 | 164 | Grand Total | 224.5% | Grand Total | 530.1% |  | Average | 27.3333 | 54.6667 | 100% | Grand Total | 92.13% | Grand Total | 13.41%

## Read (hidden)
Sprint Name | Capacity (Hrs) | Workload (Hrs) | Capacity UtIlization |  | Sprint | Committed | Delivered | Committment Reliability | Sprint | Defects during Sprint | Remaining defects after sprint | Defect Leakage.
Sprint 1 | 468 | 300 | 64.1% | Backlog Health Index | Sprint 1 | 35 | 22 | 62.86% | Sprint 1 | 15 | 11 | 73.33%
Sprint 2 | 474 | 350 | 73.84% | < Average Velocity | Sprint 2 | 25 | 28 | 112% | Sprint 2 | 10 | 6 | 60%
Sprint 3 | 462 | 450 | 97.4% | >Average Velocity and < 2 | Sprint 3 | 27 | 27 | 100% | Sprint 3 | 12 | 5 | 41.67%
Sprint 4 | 474 | 450 | 94.94% | > 2 and < 3 | Sprint 4 | 29 | 29 | 100% | Sprint 4 | 11 | 3 | 27.27%
Sprint 5 | 468 | 460 | 98.29% | >3 | Sprint 5 | 30 | 30 | 100% | Sprint 5 | 9 | 2 | 22.22%
Sprint 6 | 468 | 460 | 98.29% |  | Sprint 6 | 32 | 28 | 87.5% | Sprint 6 | 4 | 0 | 0%
Formula =(Workload/Capacity)*100 |  |  |  |  | Commitment Reliability = 100*(Delivered/Committed) |  |  |  | Defect Leakage = 100*(Demaining defects after sprint/defects during sprint)

## Dashboard
ABC Banking App Metrics
Scrum Teams
Average Velocity
27.3333
PBL Groomed Stories
70
Backlog Health Index
2.56
For any queries, please contact
Mallikarjun Naik
mv_naik@hotmail.com
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Backlog Heath Index

## Dashboard 2 (hidden)
ABC Banking App Agile Metrics
Scrum Teams
For any queries, please contact
Mallikarjun Naik (mv_naik@hotmail.com)
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## BaseData (hidden)
Program Name | Team | Iteration | Start Date | End Date | Committed SP | Injectd SP | Descoped | Delivered SP | Teamsize | Defects | Remaining Defects | Leaves | Available Capacity | Workload | Defect Leakage | Capacity Utilization
Next Generation Banking App | Goalkeepers | Sprint 1 | 2021-11-22 | 2021-12-03 | 39 | 11 |  | 33 | 8 | 15 | 10 | 3 | 462 | 400 | 0.66667 | 0.8658
Next Generation Banking App | Goalkeepers | Sprint 2 | 2021-12-06 | 2021-12-17 | 44 | 8 |  | 37 | 8 | 12 | 6 | 2 | 468 | 410 | 0.5 | 0.87607
Next Generation Banking App | Goalkeepers | Sprint 3 | 2021-12-20 | 2021-12-31 | 46 | 5 |  | 39 | 8 | 7 | 3 | 3 | 462 | 420 | 0.42857 | 0.90909
Next Generation Banking App | Goalkeepers | Sprint 4 | 2022-01-03 | 2022-01-14 | 43 | 2 |  | 41 | 8 | 4 | 0 | 1 | 474 | 450 | 0 | 0.94937
Next Generation Banking App | Goalkeepers | Sprint 5 | 2022-01-17 | 2022-01-28 | 49 | 0 | 2 | 47 | 8 | 4 | 1 | 2 | 468 | 460 | 0.25 | 0.98291
Next Generation Banking App | Goalkeepers | Sprint 6 | 2022-01-31 | 2022-02-11 | 51 | 0 |  | 51 | 8 | 4 | 0 | 3 | 462 | 460 | 0 | 0.99567
Next Generation Banking App | Sapient | Sprint 1 | 2021-11-22 | 2021-12-03 | 33 | 15 |  | 31 | 6 | 13 | 7 | 2 | 348 | 300 | 0.53846 | 0.86207
Next Generation Banking App | Sapient | Sprint 2 | 2021-12-06 | 2021-12-17 | 35 | 8 | 2 | 33 | 8 | 10 | 6 | 1 | 474 | 350 | 0.6 | 0.7384
Next Generation Banking App | Sapient | Sprint 3 | 2021-12-20 | 2021-12-31 | 34 | 5 |  | 37 | 8 | 10 | 2 | 5 | 450 | 400 | 0.2 | 0.88889
Next Generation Banking App | Sapient | Sprint 4 | 2022-01-03 | 2022-01-14 | 36 | 2 |  | 38 | 8 | 5 | 1 | 4 | 456 | 410 | 0.2 | 0.89912
Next Generation Banking App | Sapient | Sprint 5 | 2022-01-17 | 2022-01-28 | 45 | 0 | 4 | 41 | 8 | 3 | 0 | 3 | 462 | 450 | 0 | 0.97403
Next Generation Banking App | Sapient | Sprint 6 | 2022-01-31 | 2022-02-11 | 42 | 0 |  | 42 | 8 | 2 | 0 | 2 | 468 | 460 | 0 | 0.98291
Next Generation Banking App | Titans | Sprint 1 | 2021-11-22 | 2021-12-03 | 35 | 8 |  | 31 | 6 | 22 | 13 | 2 | 348 | 300 | 0.59091 | 0.86207
Next Generation Banking App | Titans | Sprint 2 | 2021-12-06 | 2021-12-17 | 32 | 5 |  | 33 | 5 | 16 | 11 | 1 | 294 | 200 | 0.6875 | 0.68027
Next Generation Banking App | Titans | Sprint 3 | 2021-12-20 | 2021-12-31 | 34 | 3 |  | 37 | 8 | 12 | 4 | 1 | 474 | 450 | 0.33333 | 0.94937
Next Generation Banking App | Titans | Sprint 4 | 2022-01-03 | 2022-01-14 | 36 | 0 |  | 36 | 8 | 11 | 3 | 2 | 468 | 450 | 0.27273 | 0.96154
Next Generation Banking App | Titans | Sprint 5 | 2022-01-17 | 2022-01-28 | 35 | 0 |  | 35 | 8 | 5 | 0 | 2 | 468 | 460 | 0 | 0.98291
Next Generation Banking App | Titans | Sprint 6 | 2022-01-31 | 2022-02-11 | 37 | 0 |  | 37 | 8 | 2 | 0 | 1 | 474 | 470 | 0 | 0.99156
Next Generation Banking App | Optimizers | Sprint 1 | 2021-11-22 | 2021-12-03 | 20 | 0 | 6 | 12 | 4 | 12 | 6 | 2 | 228 | 200 | 0.5 | 0.87719
Next Generation Banking App | Optimizers | Sprint 2 | 2021-12-06 | 2021-12-17 | 16 | 0 | 5 | 11 | 4 | 11 | 5 | 1 | 234 | 200 | 0.45455 | 0.8547
Next Generation Banking App | Optimizers | Sprint 3 | 2021-12-20 | 2021-12-31 | 17 | 0 |  | 16 | 5 | 17 | 5 | 2 | 288 | 240 | 0.29412 | 0.83333
Next Generation Banking App | Optimizers | Sprint 4 | 2022-01-03 | 2022-01-14 | 21 | 0 |  | 21 | 4 | 4 | 0 | 2 | 228 | 220 | 0 | 0.96491
Next Generation Banking App | Optimizers | Sprint 5 | 2022-01-17 | 2022-01-28 | 23 | 0 |  | 23 | 8 | 4 | 0 | 2 | 468 | 400 | 0 | 0.8547
Next Generation Banking App | Optimizers | Sprint 6 | 2022-01-31 | 2022-02-11 | 25 | 0 |  | 25 | 8 | 3 | 0 | 0 | 480 | 450 | 0 | 0.9375
Next Generation Banking App | Avengers | Sprint 1 | 2021-11-22 | 2021-12-03 | 35 | 21 |  | 22 | 7 | 15 | 11 | 1 | 414 | 300 | 0.73333 | 0.72464
Next Generation Banking App | Avengers | Sprint 2 | 2021-12-06 | 2021-12-17 | 25 | 5 |  | 28 | 8 | 10 | 6 | 1 | 474 | 350 | 0.6 | 0.7384
Next Generation Banking App | Avengers | Sprint 3 | 2021-12-20 | 2021-12-31 | 27 | 0 |  | 27 | 8 | 12 | 5 | 0 | 480 | 500 | 0.41667 | 1.0417
Next Generation Banking App | Avengers | Sprint 4 | 2022-01-03 | 2022-01-14 | 29 | 0 |  | 29 | 8 | 11 | 3 | 1 | 474 | 450 | 0.27273 | 0.94937
Next Generation Banking App | Avengers | Sprint 5 | 2022-01-17 | 2022-01-28 | 30 | 0 |  | 30 | 8 | 9 | 2 | 0 | 480 | 420 | 0.22222 | 0.875
Next Generation Banking App | Avengers | Sprint 6 | 2022-01-31 | 2022-02-11 | 32 | 0 | 4 | 28 | 8 | 4 | 0 | 2 | 468 | 455 | 0 | 0.97222
Next Generation Banking App | Solvers | Sprint 1 | 2021-11-22 | 2021-12-03 | 33 | 0 | 4 | 29 | 7 | 12 | 5 | 2 | 408 | 300 | 0.41667 | 0.73529
Next Generation Banking App | Solvers | Sprint 2 | 2021-12-06 | 2021-12-17 | 31 | 0 |  | 31 | 8 | 13 | 2 | 5 | 450 | 350 | 0.15385 | 0.77778
Next Generation Banking App | Solvers | Sprint 3 | 2021-12-20 | 2021-12-31 | 37 | 0 |  | 47 | 8 | 14 | 2 | 2 | 468 | 400 | 0.14286 | 0.8547
Next Generation Banking App | Solvers | Sprint 4 | 2022-01-03 | 2022-01-14 | 41 | 0 |  | 41 | 8 | 11 | 1 | 1 | 474 | 430 | 0.090909 | 0.90717
Next Generation Banking App | Solvers | Sprint 5 | 2022-01-17 | 2022-01-28 | 42 | 0 |  | 42 | 8 | 9 | 0 | 1 | 474 | 450 | 0 | 0.94937
Next Generation Banking App | Solvers | Sprint 6 | 2022-01-31 | 2022-02-11 | 45 | 0 |  | 42 | 8 | 8 | 0 | 2 | 468 | 450 | 0 | 0.96154
Next Generation Banking App | Spartans | Sprint 1 | 2021-11-22 | 2021-12-03 | 37 | 12 |  | 33 | 8 | 7 | 2 | 5 | 450 | 300 | 0.28571 | 0.66667
Next Generation Banking App | Spartans | Sprint 2 | 2021-12-06 | 2021-12-17 | 38 | 15 |  | 35 | 8 | 8 | 1 | 1 | 474 | 350 | 0.125 | 0.7384
Next Generation Banking App | Spartans | Sprint 3 | 2021-12-20 | 2021-12-31 | 40 | 5 |  | 41 | 8 | 4 | 1 | 2 | 468 | 405 | 0.25 | 0.86538
Next Generation Banking App | Spartans | Sprint 4 | 2022-01-03 | 2022-01-14 | 40 | 3 |  | 40 | 8 | 3 | 1 | 1 | 474 | 450 | 0.33333 | 0.94937
Next Generation Banking App | Spartans | Sprint 5 | 2022-01-17 | 2022-01-28 | 45 | 0 | 4 | 41 | 9 | 2 | 0 | 2 | 528 | 498 | 0 | 0.94318
Next Generation Banking App | Spartans | Sprint 6 | 2022-01-31 | 2022-02-11 | 45 | 0 |  | 45 | 8 | 3 | 0 | 1 | 474 | 470 | 0 | 0.99156
Next Generation Banking App | Maximizers | Sprint 1 | 2021-11-22 | 2021-12-03 | 33 | 5 |  | 34 | 8 | 12 | 6 | 2 | 468 | 300 | 0.5 | 0.64103
Next Generation Banking App | Maximizers | Sprint 2 | 2021-12-06 | 2021-12-17 | 35 | 7 |  | 35 | 8 | 8 | 4 | 1 | 474 | 350 | 0.5 | 0.7384
Next Generation Banking App | Maximizers | Sprint 3 | 2021-12-20 | 2021-12-31 | 35 | 5 |  | 36 | 8 | 7 | 2 | 3 | 462 | 450 | 0.28571 | 0.97403
Next Generation Banking App | Maximizers | Sprint 4 | 2022-01-03 | 2022-01-14 | 37 | 0 | 6 | 31 | 8 | 5 | 2 | 1 | 474 | 450 | 0.4 | 0.94937
Next Generation Banking App | Maximizers | Sprint 5 | 2022-01-17 | 2022-01-28 | 40 | 0 |  | 40 | 8 | 2 | 0 | 2 | 468 | 460 | 0 | 0.98291
Next Generation Banking App | Maximizers | Sprint 6 | 2022-01-31 | 2022-02-11 | 42 | 0 |  | 42 | 8 | 3 | 0 | 2 | 468 | 460 | 0 | 0.98291
Next Generation Banking App | Visionaries | Sprint 1 | 2021-11-22 | 2021-12-03 | 32 | 23 |  | 25 | 8 | 22 | 17 | 2 | 468 | 320 | 0.77273 | 0.68376
Next Generation Banking App | Visionaries | Sprint 2 | 2021-12-06 | 2021-12-17 | 42 | 22 |  | 32 | 8 | 10 | 5 | 3 | 462 | 350 | 0.5 | 0.75758
Next Generation Banking App | Visionaries | Sprint 3 | 2021-12-20 | 2021-12-31 | 42 | 15 |  | 37 | 8 | 8 | 2 | 1 | 474 | 400 | 0.25 | 0.84388
Next Generation Banking App | Visionaries | Sprint 4 | 2022-01-03 | 2022-01-14 | 42 | 12 |  | 43 | 8 | 5 | 1 | 2 | 468 | 420 | 0.2 | 0.89744
Next Generation Banking App | Visionaries | Sprint 5 | 2022-01-17 | 2022-01-28 | 42 | 3 |  | 42 | 8 | 3 | 0 | 3 | 462 | 450 | 0 | 0.97403
Next Generation Banking App | Visionaries | Sprint 6 | 2022-01-31 | 2022-02-11 | 50 | 0 | 5 | 45 | 8 | 2 | 0 | 4 | 456 | 450 | 0 | 0.98684

## Backlog Health (hidden)
Team | Average Velocity | Story Points in PBL | Backlog Health | Flag | Expected | Team | Team | Team | Team | Team | Team | Team | Team | Team
Goalkeepers | 41.3333 | 60 | 1.4516 | FALSE | 3 | Goalkeepers | Sapient | Titans | Optimizers | Avengers | Solvers | Spartans | Maximizers | Visionaries
Sapient | 37 | 50 | 1.3514 | FALSE | 3
Titans | 34.8333 | 20 | 0.57416 | FALSE | 3 | Flag
Optimizers | 18 | 5 | 0.27778 | FALSE | 3 | TRUE
Avengers | 27.3333 | 70 | 2.561 | TRUE | 3
Solvers | 38.6667 | 60 | 1.5517 | FALSE | 3
Spartans | 39.1667 | 80 | 2.0426 | FALSE | 3
Maximizers | 36.3333 | 90 | 2.4771 | FALSE | 3
Visionaries | 37.3333 | 60 | 1.6071 | FALSE | 3
| Velocity | PBL Groomed SP | Backlog Health
| 27.3333 | 70 | 2.561

## Speedometer (hidden)
Label | RAG | Value
<AV | 30 | 76.8293
1XAV | 30 | 1
2XAV | 30 | 122.1707
3XAV | 30
Backlog Health 2.56 | 80