## User Stories
JIRA ID | Summary | Effort 1-5 | Complexity 1-5 | Uncertainity 1-5 | Fibonnacci | Description | RAG
SFZ-50 | Configure Cloud Products in salesforce | 5 | 3 | 3 | 8 | Consider Splitting | 8
JIRA-ID 2 | Story 2 | 5 | 5 | 5 | 13 | Splitting required | 13
JIRA-ID 3 | Story 3 | 5 | 5 | 5 | 13 | Splitting required | 13
JIRA-ID 4 | Story 4 | 5 | 2 | 5 | 8 | Consider Splitting | 8
JIRA-ID 5 | Story 5 | 1 | 1 | 1 | 1 | Rightly sized | 1
JIRA-ID 6 | Story 6 | 1 | 5 | 1 | 3 | Rightly sized | 3
JIRA-ID 7 | Story 7 | 1 | 1 | 1 | 1 | Rightly sized | 1
JIRA-ID 8 | Story 8 | 1 | 1 | 1 | 1 | Rightly sized | 1
JIRA-ID 9 | Story 9 | 1 | 1 | 1 | 1 | Rightly sized | 1
JIRA-ID 10 | Story 10 | 1 | 1 | 1 | 1 | Rightly sized | 1
JIRA-ID 11 | Story 11 | 1 | 1 | 1 | 1 | Rightly sized | 1

## Story Point Reference
CRE Sum | Story Points | Description | Effort | Rating | Complexity | Rating | Risk | Rating
3 | 1 | Rightly sized | 1Hr-8hr | 1 | XS | 1 | No Risks | 1
4 | 1 | Rightly sized | 8Hr-to 12 Hr | 2 | S | 2 | Low | 2
5 | 2 | Rightly sized | 12Hr-20Hr | 3 | M | 3 | Medium | 3
6 | 2 | Rightly sized | 20Hr-30 Hrs | 4 | L | 4 | High | 4
7 | 3 | Rightly sized | 30Hr-40H | 5 | XL | 5 | Critical | 5
8 | 3 | Rightly sized
9 | 5 | Rightly sized
10 | 5 | Rightly sized
11 | 8 | Consider Splitting
12 | 8 | Consider Splitting
13 | 8 | Consider Splitting
14 | 13 | Splitting required
15 | 13 | Splitting required